## Agenda
Meeting Agenda: Program Diaspora Berdampak, September Visit Planning
Date:26/08/2026 Attendees: Dr Desy Nuryunarsih, Dr Upik Rahmi
# | Agenda Item | Notes | Suggested Framing / Talking Point
1 | Quick recap of the schedule | Confirm the revised 3 days plan (8 to 10 September) is locked, so everything else in the meeting is anchored to real dates.
2 | Hotel and local transport, arranging it directly | Ask for the budgeted amounts so travel and accommodation can be booked directly rather than arranged by the institution. This also naturally resolves the earlier transparency question without needing to raise it separately. | Since the visit is now 4 days rather than 14, I would like to arrange my own hotel and local transport directly so I can plan around the session times. Could you share what has been allocated for accommodation and vehicle so I can book accordingly?
3 | Ethics approval status | Ask where the ethics submission stands for the pre and post evaluation, and what is still needed. Worth asking directly whether data collection can proceed if approval is not through by the visit date, since that is the one item with a hard deadline risk. | I have drafted a full ethics protocol, information sheet, and consent form already, happy to send those over today if useful. Where are we with submission to the ethics committee, and is there a realistic timeline before September?
4 | Laptops for Day 2 training | Confirm whether the venue or UPI can provide laptops for participants, since the hands on Jupyter Notebook session depends on it. If laptops cannot be guaranteed, agree on a Google Colab fallback plan now rather than day of. | For Day 2's hands-on session, participants will need a laptop each to install Jupyter and follow along. Can UPI provide laptops, or should I send a bring your own laptop instruction to participants in advance, along with my install video?
5 | Walk through the GitHub project | Show the pre and post materials already in the repository: questionnaire, consent form, information sheet, data entry template, sample data, and analysis script. Confirm who else needs access, likely Dr Upik and the two dosen who will be writing the manuscript.
6 | Confirm Day 2 content: data preparation | Briefly confirm the plan: the install video goes out ahead of time, then the live session covers hands on data preparation using the sample code already in GitHub. This is a shared understanding check rather than a discussion item.
7 | Next steps and owners | Close by naming who does what before September: ethics submission, laptop confirmation, sending the install video, and by when.
Action Items (fill in during the meeting)
# | Action | Owner | By When
1
2
3
4
5
6
7